DRAFT

Capital Improvements Program for 2007 through 2016

Greenfield, New Hampshire

September 29, 2006

DRAFT

Table of Contents

Page

Executive Summary									3

Introduction										7

Definition of Capital Projects								7

CIP Committee									8

CIP Milestones									8

Department Interviews								9

Capital Projects Proposed by Greenfield’s Operating Departments			10

Historical and Fiscal Analysis								12

CIP Committee’s Recommendations							12

Appendix A - Introductory Letter Sent to Department Heads			15

Appendix B - Worksheet								16

Appendix C - Summary of Capital Expenditures 1996 - 2005			18

Appendix D - Projects Covered by Capital Expenditures 1996 - 2005		19

Appendix E - Capital projects proposed by department heads for 2007 - 2016	20

Police Department								20

Fire Department								21

Town Clerk									24

Tax Collector									24

Administrative Department							25

Library										26

Parks and Recreation								27

Highway Department - Roads						28

DPW - Facilities								30

DPW - Vehicles								31

Recycling Center								32

Appendix F - Projects recommended by the CIP committee for 2007 - 2016	34

with a priority of ‘Urgent’

Appendix G - Projects recommended by the CIP committee for 2007 - 2016	35

with a priority of ‘Urgent’ plus a priority of ‘Necessary’

Appendix H - References								36

Executive Summary:

This summary presents an overview of the process, findings and recommendations for an update to Greenfield’s Capital Improvements Program.  Details will be found in subsequent sections of this report.

Introduction:

A Capital Improvements Program (CIP) update has been created for the Town of Greenfield, NH by the Greenfield Planning Board’s CIP Committee.  New Hampshire statutes provide for the creation of a CIP when certain requirements have been met by the municipality; Greenfield has satisfied those requirements.  The updated CIP covers the period 2007 through 2016.

The CIP addresses these primary goals:

- Anticipate capital expenditures during the time frame of the CIP and help minimize spikes in the timing of those expenditures.

- Help minimize major fluctuations in the Town’s portion of property taxes.

- Provide a basis, along with our Master Plan and Impact Fee Ordnance, to levy Impact Fees should the town choose to do so.

- Assist in the preparation of annual town budgets.

Capital projects for a NH town the size of Greenfield are defined as “any expenditure for a project or facility having a useful life of at least three years, requiring a gross expenditure of at least $5,000 and creating a depreciable asset”.

Process:

The CIP committee began its work in June, 2006 with the creation of a CIP project plan, updating the questionnaire to be used in interviewing the town departments and assignment of committee members to interview department heads.

During July, information was obtained from each department head detailing the capital projects they’re proposing for the period 2007 through 2016.  This data was entered into a spreadsheet and analyzed by the CIP committee / Planning Board.  In addition, historical data on capital expenditures was updated to include the period 1996 - 2005 for comparison purposes.

Meetings were held in July, August and September at which the department heads, budget advisory committee and the public were invited to attend.

Finally, priorities and recommended implementation time frames were assigned by the CIP Committee / Planning Board to each proposed capital project.  It is expected that in October, the CIP will be adopted by vote of the Planning Board and a summary prepared for presentation to the Board of Selectmen in November.

CIP Committee’s Findings and Recommendations:

- Initially, capital projects proposed by Greenfield’s operating departments for the period 2007 through 2016 totaled $4,528,239.  After review and assignment of priorities by the CIP Committee, the ‘Urgent’ projects were reduced to a total of $735,549 or 16.2% of the initial requests.  The ‘Urgent’ plus ‘Necessary’ priority projects totaled $3,547,970 or 78.4% of the initial requests.  These two priorities were defined as follows:

Urgent		“Cannot be delayed.  Needed for health or safety.”

Necessary	“Needed to maintain existing level and quality of community services.  Needed

within one to three years.”

Definitions of the remaining priorities will be found on page 10 of this document.  A list of the projects having an ‘Urgent’ or ‘Necessary’ priority will be found on page 12 of this document.

All projects proposed by the various departments are detailed in Appendix E of this document.

- All projections for 2007 through 2016 include an estimated 3% annual rate of inflation.

- All projects recommended by the CIP committee with a priority of ‘Urgent’ or ‘Necessary’ are to replace existing facilities or vehicles with a few exceptions detailed later in this document.

- The CIP committee recommends that all vehicles be purchased through a lease-purchase arrangement with the costs spread over a four year period.

- All lease-purchases and proposed bond issues include a 6% annual rate of interest.

- Various projects may be funded through specific grants available.  Where these funding sources have been identified, they are shown with the individual projects in Appendix E.  Funding for other recommended capital projects may be provided by a bond or other sources being investigated.

- Following is a comparison of selected capital projects.

1996 - 2005	Actual capital expenditures for 1996 - 2005		$1,082,102

(less road maintenance)

2007 - 2016	Recommended projects with ‘Urgent’ priority		   $735,549

(road maintenance not in this category)

2007 - 2016	Recommended projects with				$2,381,839

‘Urgent’ + ‘Necessary’ priorities (less road

maintenance)

- Some projects listed on last year’s CIP as ‘Urgent’ were re-prioritized as ‘Necessary’ to more accurately reflect the definition of the priorities and true urgency of those projects.

- Following are per-capita calculations to show how these capital expenditures compare with the projected population growth.

Period		Population year	Estimated	Per-capita capital expenses

Used for calculations	Population

1996 - 2005		2000		1,657		$653.05

(actual capital expenditures)

2007 - 2016		2010		1,900		$387.13

(‘Urgent’ priority only)

2007 - 2016		2010		1,900		$1,253.60

(‘Urgent’ + ‘Necessary’ priorities)

| Department | Est Cost in 2006 $ | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Police | $123,188 |  | $8,169 | $8,659 | $17,851 | $18,918 | $9,744 | $19,795 | $10,038 | $20,692 | $21,930 | $135,796 |
| Fire | $585,225 | $20,214 | $68,238 | $72,332 | $76,700 | $133,499 | $55,362 | $58,704 | $62,204 | $102,198 | $22,842 | $672,293 |
| Town Clerk | $8,250 | $8,498 |  |  |  |  |  |  |  |  |  | $8,498 |
| Tax Collector | $8,250 | $8,498 |  |  |  |  |  |  |  |  |  | $8,498 |
| Admin | $108,094 | $111,337 |  |  |  |  |  |  |  |  |  | $111,337 |
| Library | $11,180 | $11,515 |  |  |  |  |  |  |  |  |  | $11,515 |
| Highway - Roads | $1,059,875 | $188,490 | $202,253 | $250,024 | $257,573 | $176,748 | $91,043 |  |  |  |  | $1,166,131 |
| DPW - Facilities | $737,000 |  | $143,235 | $139,576 | $61,057 | $64,721 | $68,604 | $72,720 | $77,083 | $81,708 | $86,611 | $795,315 |
| DPW - Vehicles | $549,200 | $57,191 | $60,623 | $97,073 | $80,759 | $36,856 | $79,351 | $42,716 | $45,279 | $71,446 | $24,857 | $596,151 |
| Recycling Center |  |  |  |  |  |  |  |  |  |  |  |  |
| Parks and Recreation | $41,200 | $42,436 |  |  |  |  |  |  |  |  |  | $42,436 |
| Total | $3,231,462 | $448,179 | $482,518 | $567,664 | $493,940 | $430,742 | $304,104 | $193,935 | $194,604 | $276,044 | $156,240 | $3,547,970 |

Introduction:

This report documents the update to the Capital Improvements Program (CIP) for Greenfield, New Hampshire.  New Hampshire RSA 674:5 provides for the creation and updating of a CIP if approved by the voters of the town.  Greenfield approved the creation of a CIP in a warrant article by town vote in 1996.  Greenfield’s last CIP covered the period 2006 through 2015 and the current update covers the period 2007 through 2016.

In addition to specifically authorizing a CIP as noted above, the State of New Hampshire requires that the municipality have a current Master Plan.  Greenfield created a Master Plan in 2003 thus satisfying the requirements to produce a CIP.

The CIP committee’s recommendations may be found in the section entitled CIP Committee Recommendations beginning on page 12.

A Capital Improvements Program has a number of significant purposes.  Among them are 1:

- Provide a link between the Town’s Master Plan goals, land use ordnances and economic development.

- Bridge the gap between planning and spending.

- Minimize the use of stop-gap measures to fund public health, safety and welfare activities.

- Anticipate investments in community facilities needed to shape the pattern of growth and development in Greenfield.

- Improve coordination and communication between town departments by identifying and sharing information relative to each department’s needs.  An example of this is the possible future relocation of the Town’s Police, Town Clerk, Tax Collector and Recreation Department facilities.

- Avoid undue sudden tax increases by promoting discussion of new capital expenditures over time.

- Develop a fair distribution of capital costs by promoting public discussion on the means of funding capital projects.

- Build a foundation for impact fees and/or growth management ordnances should the town decide to enact either or both.

- Support economic development by demonstrating a sound fiscal plan for the town.

Definition of Capital Projects:

The Southern New Hampshire Planning Commission suggests the following definition of a capital project for small towns in New Hampshire 1:

“Any expenditure for a project or facility having a useful life of at least three years and requiring a gross expenditure of at least $5,000.”

The Commission further stated that: “Generally, a capital project creates a depreciable asset, while operating costs relate to expenses of delivering services to persons or properties, and the cost of operating and maintaining fixed capital assets”

Greenfield’s CIP committee was guided by those criteria in the preparation of the CIP.

CIP Committee:

In June, 2006, the Greenfield Planning Board established a committee empowered to create a Capital Improvements Program for Greenfield and to have the CIP updated annually.

Greenfield’s CIP committee is comprised of the following members:

Mike Borden

Dario Carrara, Planning Board Chairman

Marilyn Fletcher

John Halper, CIP Committee Chairman

Gil Morris

Kevin O’Connell

Sheldon Pennoyer

George Rainier

CIP Milestones:

Greenfield’s CIP was created during the period June, 2006 through September, 2006.  During that time the following were accomplished:

- CIP Committee formed - 6/12/06.

- CIP committee members assigned to conduct departmental CIP interviews - 6/12/06.

- Questionnaire and worksheet to be used for departmental CIP interviews created - 6/19/06.

- Formation of CIP committee announced on the town’s web site and in the ‘Greenfield Spirit’ (8/06 issue); volunteers requested - 6/22/06.

- Letter sent to department heads notifying them that a CIP committee member would contact them to gather CIP data for their department - 6/21/06.

- Capital improvements and annual operating expenditures data collection for the period covering the past 10 years completed - 7/1/06.

- Departmental CIP interviews completed - 7/24/06.

- Initial CIP data spreadsheet completed - 8/7/06.

- Initial CIP data presented to planning board members during planning board meeting - 8/14/06.

- CIP data revised to reflect changes suggested during 8/14/06 Planning Board meeting - 8/21/06.

- Review of town’s Master Plan for information relevant to the CIP completed - 8/28/06.

- CIP data presented to the department heads and the public during Planning Board meeting - 8/28/06.

- CIP data revised to incorporate changes from the 8/28/06 meeting and establish priorities for the proposed projects - 9/11/06.

- CIP draft written - 9/18/06 through 9/29/06.

- CIP draft submitted to Planning Board members for initial review - 10/2/06. [Anticipated date]

- CIP draft posted on the town’s web site - 10/9/06. [Anticipated date]

- Public hearing on the CIP held - 10/16/06. [Anticipated date]

- Planning board final review and vote to adopt the CIP - 10/23/06. [Anticipated date]

- CIP summary prepared for presentation to Board of Selectmen on 10/26/06. [Anticipated date]

Department Interviews:

Each of Greenfield’s department heads was interviewed by a CIP Committee member to ascertain the projects that each department believes are necessary for its proper operation.  Departments not projecting capital expenditures exceeding $5,000 were not included.

Prior to the interview, an introductory letter was sent to each department head advising them of the need for the CIP and informing them that they would be contacted by a member of the committee to conduct the interview.  A copy of the letter will be found in Appendix A.

A worksheet for gathering the details of each project during the interviews was prepared and attached to the introductory letter.  A copy of the worksheet format is included as Appendix B.

Each of the interviewers utilized the worksheet as a guide to obtaining the necessary details during the interviews.  This technique relieved the department heads of the need to complete the forms in advance and provided a consistent approach to gathering the data.  All the interviewers attended a committee meeting during which instructions were developed for conducting the interviews.

The detailed worksheets completed by each department may be viewed at the town office.

Following are the committee members conducting the interviews and the department heads and/or other departmental staff members interviewed:

Department		CIP Committee member	Person(s) Interviewed

Fire	John Halper			Chief Loren White

Deputy Chief Jim Plourde

Police			John Halper			Chief Brian L. Giammarino

Town Clerk		Gilbert Morris			Edith "Dee" Sleeper

Tax Collector		Gilbert Morris			Laurie May

Administrative		Gilbert Morris			Deb Davidson

Catherine Shaw

Library			Marilyn Fletcher		Peter Wensberg

Mary Ann Grant

Highway		Kevin O’Connell		Wyatt ‘Duffy’ Fox II

John Halper

DPW - Facilities /	Sheldon Pennoyer		Wyatt ‘Duffy’ Fox II

Vehicles

Recycling		Mike Borden			Franklin Pelkey

Parks and		George Rainier		Molly Anfuso

Recreation

Capital Projects Proposed by Greenfield’s Operating Departments:

Each of the capital projects proposed by the operating departments was presented at a public meeting and subsequently reviewed and discussed by the CIP committee.  The committee assigned a priority to each project in accordance with New Hampshire RSA 674:6.

The priorities used by the committee are defined below.  These priorities were derived from reference 1 and from the CIP’s created by a sample of other small New Hampshire towns.

U = Urgent		Cannot be delayed.  Needed for health or safety.

C = Committed	Part of an existing contractual agreement or otherwise legally required.

N = Necessary	Needed to maintain existing level and quality of community services.  Needed within 1 to 3 years.

D = Desirable	Needed to improve quality or level of services.  Needed within 4 to 6 years.

F = Deferrable	Can be placed on hold until after 6 years, but supports community development goals.

R = Research	Pending results of ongoing research, planning and coordination.

I = Inconsistent	Conflicts with an alternative project or solution recommended by the CIP; contrary to land use planning or community development goals.

Note: Greenfield plans to review its CIP annually; this document presents the results of the first annual review.

The projects proposed by each department are shown in Appendix E.  The project elements included for each are:

Project				Name of project

Acquisition Year Requested	Time frame requested by the department and is not necessarily the same time frame recommended by the CIP Committee.

Anticipated Lifespan		(self-explanatory)

CIP Priority	Priority assigned to the project by the CIP Committee (see above) and is not necessarily the same priority requested by the department.

Estimated Cost	Estimated cost for the project as adjusted for an annual inflation rate of 3.0%.  Lease-purchases are spread over a four-year period with a 6% annual rate of interest.  Bonds are spread over a ten-year period with a 6% annual rate of interest.

Possible Funding Source:	If included, this element notes possible funding sources suggested by the department or by the CIP Committee.

CIP Recommendation		(self-explanatory)

Comments	Other notes from the CIP committee and the requesting department relative to the project.

Historical and Fiscal Analysis:

Although optional for a New Hampshire CIP, the committee tabulated Greenfield’s population history and projected growth for the period 1970 through 2020 and examined its capital and budgetary expenditures for the past ten years.  This was done to establish a perspective for the proposed projects as compared to past expenditures.

Population history 2, 3 and projected growth 4 for Greenfield.

| Year | 1970 | 1975 | 1980 | 1985 | 1990 | 1995 | 2000 | 2005 | 2010 | 2015 | 2020 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Population | 1058 | 1026 | 972 | 1322 | 1519 | 1559 | 1657 | 1790 | 1900 | 2010 | 2100 |
| % Change |  | -3.0 | -5.3 | +3.6 | +1.5 | +2.6 | +6.3 | +8.0 | +6.1 | +5.8 | +4.5 |

Capital expenditures in Greenfield for the period 1996 through 2005 totaled $1,150,290 and are shown in Appendix C.  Note: road resurfacing / maintenance were not included in the historical data obtained.  The specific projects covered by the 1996 - 2005 expenditures are shown in Appendix D.

CIP Committee’s Recommendations:

The CIP Committee’s recommendations are summarized in this section.  Details of each project, including those requested by each department whether ultimately recommended or not recommended by the CIP Committee are shown in Appendix E.

Year-by-year totals of the capital projects for 2007 through 2016 having a priority of ‘Urgent’ and those having priorities of ‘Urgent’ + ‘Necessary’ are shown in Appendixes F and G respectively.

Initially, capital projects proposed by Greenfield’s operating departments for the period 2007 through 2016 totaled $4,528,239.  After review and assignment of priorities by the CIP Committee, the ‘Urgent’ projects were reduced to a total of $735,549 or 16.2% of the initial requests.  The ‘Urgent’ plus ‘Necessary’ priority projects totaled $3,547,970 or 78.4% of the initial requests.

Following are the projects recommended by the CIP committee having a priority of ‘Urgent’ or ‘Necessary’.

Department	Project					Priority 	Estimated	Year

Cost

Police		Replace cruiser			U		$35,739	2008 (**)

Police		Replace cruiser			N		$37,927	2010 (**)

Police		Replace cruiser			N		$41,431	2013 (**)

Police		Replace cruiser			N		$20,699 (*)	2015

Fire		Replace pagers			U		$12,875	2007

Fire		Replace fire hose			U		$7,339		2007

Fire		Replace fire engine #1		U		$298,541	2008 (**)

Fire		Replace tanker			N		$228,498	2011

Fire		Replace rescue vehicle		N		$24,228 (*)	2015

Fire		Replace extrication equipment	N		$20,162	2015

Fire		Replace turn-out gear (PPE)		U		$60,487	2015

Fire		Vehicle for full-time fire chief		N		$20,163 (*)	2015

Department	Project					Priority 	Estimated	Year

Cost

Town Clerk	Fire-proof record storage cabinets	U		$8,498		2007

Tax Collector	Fire-proof record storage cabinets	U		$8,498		2007

Admin		Replace windows in town offices	N		$22,963	2007

Admin		Replace boiler & upgrade HVAC	U		$61,852	2007

Admin		Parking lot lights			U		$5,304		2007

Admin		Redo walkway from parking lot	U		$21,218	2007

Library		Shelving in office, workroom, etc.	N		$6,365		2007

Library		Inspect and recommend roof maint.	U		$5,150		2007

Parks & Rec	Oak Park playground improvements	U		$42,436	2007

Highway	Road resurfacing / maintenance	N		(varies)	2007-2012

(see Appendix E for details)

DPW facilities	Salt and sand storage building	N		$143,235	2008

DPW facilities	Security fencing			N		$81,975	2009

DPW facilities	New Highway Department building	N		$576,011	2009 (****)

DPW vehicles	Replace F550				U+C		$59,114	2007 (***)

DPW vehicles	Replace Caterpillar 920 loader	U		$168,985	2007 (**)

DPW vehicles	Replace Caterpillar 4WD backhoe	U		$143,456	2009 (**)

DPW vehicles	Replace Intl tandem dump truck	U		$176,289	2012

DPW vehicles	Mt. trackless (sidewalk tracks)	U		$48,307 (*)	2015

Notes:

- (*) Cost in ‘2006 dollars’; only a portion of the total cost for these projects will be incurred during the period of this CIP (2007 through 2016).

- (**) Total amount for a four-year lease-purchase.  The amount is shown in the initial year of purchase.

- (***) Amount shown is last three years of four-year lease-purchase

- (****) Total amount for a ten-year bond-type purchase.  The amount is shown in the initial year of purchase.

- All projections for 2007 through 2016 in this report include an estimated 3% annual rate of inflation.

- All projects recommended by the CIP committee with a priority of ‘Urgent’ or ‘Necessary’ are to replace existing facilities or vehicles with the exception of adding a vehicle for a future full-time Fire Chief, adding fire-proof record storage cabinets for the town clerk and for the tax assessors offices, adding parking lot lights at the town office building, shelving at the library, required improvements to the Oak Park playground, security fencing and salt/sand shed at the DPW.

- The CIP committee recommends that all vehicles be purchased through a lease-purchase arrangement with the costs spread over a four year period.  A 6% annual interest rate was used in the calculations.

- The CIP committee recommends that the new DPW building be purchased through a bond issue with the costs spread over a ten year period.  A 6% annual interest rate was used in the calculations.

- Various projects may be funded through specific grants available.  An example is funding for the equipment necessary to outfit new police cruisers.  In the instances where these funding sources have been identified, they are shown with the individual projects in Appendix E.

- Funding for other recommended capital projects may be provided by a bond or other sources being investigated.  The new Highway Department building is specifically recommended to be funded by a bond issue.

Following is a comparison of selected capital projects.

1996 - 2005	Actual Expenditures					$1,082,102

(less road maintenance)

2007 - 2016	Recommended projects with ‘Urgent’ priority		   $735,549

(road maintenance not in this category)

2007 - 2016	Recommended projects with				$2,381,839

‘Urgent’ + ‘Necessary’ priorities (less road

maintenance)

Following are per-capita calculations to show how these capital expenditures compare with the projected population growth.

Period		Population year	Estimated	Per-capita capital expenses

Used for calculations	Population

1996 - 2005		2000		1,657		$653.05

(actual capital expenditures)

2007 - 2016		2010		1,900		$387.13

(‘Urgent’ priority only)

2007 - 2016		2010		1,900		$1,253.60

(‘Urgent’ + ‘Necessary’ priorities)

Appendix A - Introductory Letter Sent to Department Heads

From:		Greenfield Planning Board

To:		Greenfield Department Heads

Re:		Greenfield Capital Improvements Plan

Date:		June 21, 2006

_______________________________________________

(Department)

Consistent with RSA 674:5-8 and our obligations as a Planning Board, we are responsible for updating Greenfield’s Capital Improvements Plan (CIP). The CIP has several important functions:

- Help the Town anticipate impending expenditures during the life of the plan.

- Help the Town stabilize major fluctuations in the town portion of the property tax.

- Help provide the basis, along with an updated Master Plan and Impact Fee Ordinance (both of which are currently in place), for levying an impact fee on future development should the Town choose to do so.

- Assist budget developers in anticipating expenses and preparing budgets

- Identify potential impact on town resources due to anticipated growth

Our current CIP was created in 2005. The task we now face is to:

- Review the Master Plan to assure that proposed expenditures are consistent with Master Plan goals adopted in 2003.

- Gather historical data on spending by the Town.

- Identify the needs of each department for capital expenditure for the foreseeable future.

The CIP Handbook (1994) defines a Capital Improvement (for a small town) as

"Any expenditure for a project or facility having a useful life of at least three (3) years and requiring a gross expenditure of at least $5,000."

The Handbook also states:

“Generally, a capital project creates a depreciable asset, while operating costs relate to expenses of delivering services to persons and properties, and the cost of operating and maintaining fixed capital assets.”

Our goal is to update our current CIP, present it to the Public and the Selectmen (including the Budget Advisory Committee) and subsequently make a recommendation to the Town regarding the value/feasibility of implementing an impact fee at the 2007 Town Meeting.   To this end, we would like to meet with you individually to hear your needs and perspectives. Attached, you will find a worksheet that will be the basis of the interview.  Please feel free to add any additional suggestions or recommendations you have to meet the needs of the Town.

__________________________________ has volunteered to meet with you sometime between June 26 and July 24, 2006.  They will contact you to arrange a mutually agreeable time to meet. Thank you in advance for your time and expertise.

Respectfully,

_________________________

John Halper

Chairman, Greenfield Capital Improvements Plan

Vice-Chairman, Greenfield Planning Board

Appendix B - Worksheet

Town of Greenfield, NH - Capital Improvements Program Update - 2007 CIP (prepared mid-2006)

Proposed Capital Project - Preliminary Worksheet

(submit each proposed project on a separate form)

Department: 	________________________________________	Date Prepared:	_________________

Department Priority: _____ of _____ total department projects

_________________________________________________________________________________________

General:

Brief description of project:	________________________________________________________

(e.g. rescue vehicle, park building, etc.)		(describe fully in ‘Project Description’ section below)

Projected acquisition date:	____________		Anticipated lifetime in years:	___________

_________________________________________________________________________________________

Nature of project (check one):

Primary effect of project is to:

_____	Replace or repair existing		_____	Provide new facility

facilities or equipment				or service capacity

_____	Improve quality of existing		_____	Expand capacity of

facilities or equipment				existing facilities or equipment

_____	Other (specify below)

_________________________________________________________________________________________

Project description:

_________________________________________________________________________________________

Rationale for project: (check all those that apply and elaborate in the ‘Narrative Justification’ section below)

_____	Removes imminent threat		_____	Alleviates substandard conditions or deficiencies

to public health or safety

_____	Responds to federal or state		_____	Improves the quality of existing services

requirement to implement

_____	Reduces long-term operating costs	_____	Provides added capacity to serve growth

(Be sure to check this item if it applies)

_____	Eligible for matching funds available	_____	Provides incentive to economic development

for limited time

Narrative Justification for Project: (If anticipated town growth is a factor, please elaborate on that as well).

_________________________________________________________________________________________

Cost Estimate: (itemize as necessary)

Capital Costs (in current $)			Impact on Operating & Maintenance

Costs or Personnel Needs (check all that apply)

Planning / feasibility analysis	$__________

Architecture & engineering fees	$__________			_____	Add Personnel

Real estate acquisition		$__________			_____	Reduce personnel

Site preparation			$__________			_____	Increase ops & maint costs

Construction			$__________			_____	Decrease ops & maint costs

Furnishings & equipment	$__________

Vehicles & capital equipment	$__________

Other ___________________	$__________

Other ___________________	$__________

==========

Total project cost	$__________

_________________________________________________________________________________________

Anticipated Source(s) of Funding:

Grant:				$__________		User fees and charges:		$__________

Loan:				$__________ 		Capital reserve withdrawal:	$__________

Impact fee account:		$__________		Current revenue:		$__________

General obligation bond:	$__________		Revenue bond:			$__________

Special assessment:		$__________

Other: ________________________________ 		$__________

_________________________________________________________________________________________

Form Prepared By (Department Member):	___________________________	Date _____________

Reviewed By (CIP Committee Member):		___________________________	Date _____________

Appendix C - Summary of Capital Expenditures 1996 - 2005

Capital expenditures in Greenfield for the period 1996 through 2005 are shown below.  Note: road resurfacing / maintenance were not included in the historical data obtained.

| Capital Expenditures | 1996 | 1997 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Police | 0 | 0 | 24,961 | 0 | 0 | 0 | 0 | 10,123 | 7,008 | 12,662 | 54,754 |
| Fire | 0 | 0 | 96,100 | 0 | 0 | 0 | 0 | 30,545 | 24,471 | 123,215 | 274,331 |
| Highway | 32,235 | 0 | 8,857 | 21,000 | 21,000 | 21,000 | 50,851 | 73,788 | 103,270 | 99,545 | 431,546 |
| Parks & Rec | 0 | 0 | 0 | 0 | 0 | 15,425 | 0 | 38,355 | 0 |  | 53,780 |
| Library | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |
| Recycling | 0 | 0 | 0 | 0 | 8,970 | 0 | 0 | 0 | 44,000 | 1,000 | 53,970 |
| Gen’l Gov’t | 11,6700 | 0 | 107,273 | 33,000 | 40,000 | 55,500 | 0 | 0 | 0 | 34,466 | 281,909 |
| Total | 43,905 | 0 | 237,209 | 54,000 | 69,970 | 91,925 | 50,851 | 114,456 | 178,749 | 270,888 | 1,150,290 |

The specific projects covered by the above past expenditures are shown in Appendix D.

Appendix D - Projects Covered by Capital Expenditures 1996 - 2005

The individual projects covered by capital expenditures during the period 1996 - 2005 are as follows.  Note that expenditures for certain projects extended over a period or years.  For example the backhoe purchased by the Highway Department was paid for over the period 1999 - 2002.

| Capital Projects | 1996 | 1997 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Police |  |  | Cruiser |  |  |  |  | Cruiser | Cruiser | Cruisers |
| Fire |  |  | Fire Truck |  |  |  |  | Generator |  | Prot. & SCBA |
| Highway | One Ton Truck |  | Sander | Backhoe | Backhoe | Backhoe | Backhoe, Dump Truck | Dump Truck, Grader, Trackless | Dump Truck, Grader, Intl Dump Truck, Trackless | Dump Truck, Grader, Intl Dump Truck, Trackless |
| Parks & Rec |  |  |  |  |  | Irrigation |  | Oak Park Bldg |  |  |
| Library |  |  |  |  |  |  |  |  |  |  |
| Recycling |  |  |  |  | Compactor, Repair Bldg |  |  |  | Bldg Expan, Fork Lift, Oil Burner | Paving |
| Gen’l Gov’t | Common Sign, Cupola, Oak Park Water, Sidewalk |  | Purchase Property | Cemetery Wall, Computers | Buy Property | Cemetery Wall, Paint Bldgs, Paving |  |  |  |  |

Appendix E - Capital projects proposed by department heads for 2007 - 2016

Following are the projects proposed and the priority levels assigned to each project by the CIP committee.

Police Department

Project:			Replace existing police cruiser

Acquisition Year Requested:	2008

Anticipated Lifespan:		4 to 5 years

CIP Priority:			Urgent

Estimated Cost:		$35,739

CIP Recommendation:	Purchase the vehicle in 2008 under a lease-purchase plan spreading the payments over four years beginning in 2008.

Comments:	Existing cruiser purchased new in 2003.  Currently has in excess of 60,000 miles on it.  Approximately 20,000 miles per year are being added to Greenfield’s police cruisers.  Chief Giammarino estimates an expected police cruiser lifetime of four to five years for a town the size of Greenfield.  Approximately 1/3 of the cost is to equip the vehicle; Chief Giammarino believes the equipment costs can be covered by NH State’s “Car 54 Project” grants.  The chief also feels that an additional police office will be needed in Greenfield in three to four years.

Project:			Replace police cruiser

Acquisition Year Requested:	2010

Anticipated Lifespan:		4 to 5 years

CIP Priority:			Necessary

Estimated Cost:		$37,927

CIP Recommendation:	Purchase the vehicle in 2010 under a lease-purchase plan spreading the payments over four years beginning in 2010.

Comments:	Existing cruiser purchased new in 2005.  Currently has in excess of 20,000 miles on it.  (Also see comments for “Replace existing police cruiser in 2008” project above).

Project:			New Police Department facility

Acquisition Year Requested:	2010

Anticipated Lifespan:		30 to 40 years

CIP Priority:			R + D

Estimated Cost:		$52,190

CIP Recommendation:	Desirable project to implement, but requires additional research.  Chief Giammarino suggested that the old town office building on Francestown Rd. be renovated and the Police Department moved there.  Police Department requires more space to be able to separately restrain parties in domestic disputes, file juvenile and adult records separately as required by statute, etc.

Comments:	Chief Giammarino suggested that the Town Clerk’s office could be moved to the existing Police Department facility.  The Town Clerk agreed that this could be a viable option.  Additional research is required.

Project:			Replace police cruiser

Acquisition Year Requested:	2013

Anticipated Lifespan:		4 to 5 years

CIP Priority:			Necessary

Estimated Cost:	$41,431

CIP Recommendation:	Purchase the vehicle in 2013 under a lease-purchase plan spreading the payments over four years beginning in 2013.

Comments:	To replace cruiser to be purchased in 2008.  (Also see comments for “Replace existing police cruiser in 2008” project above).

Project:			Replace police cruiser

Acquisition Year Requested:	2015

Anticipated Lifespan:		4 to 5 years

CIP Priority:			Necessary

Estimated Cost:	$20,699 + third and fourth year’s payments subsequent to 2016 (beyond the range of this CIP)

CIP Recommendation:	Purchase the vehicle in 2015 under a lease-purchase plan spreading the payments over four years beginning in 2015.

Comments:	To replace cruiser to be purchased in 2010.  (Also see comments for “Replace existing police cruiser in 2008” project above).

Fire Department

Project:			Replace pagers

Acquisition Year Requested:	2007

Anticipated Lifespan:		10 years

CIP Priority:			Urgent

Estimated Cost:		$12,875 (for 25 pagers, department has 28-30 members)

CIP Recommendation:	Replace pagers as requested by the Fire Department.

Comments:	Current pagers range from 6 to 20 years old and require servicing after approximately five years (about $60 per servicing).

Project:			Replace fire hose

Acquisition Year Requested:	2007

Anticipated Lifespan:		10 years

CIP Priority:			Urgent

Estimated Cost:	$7339 (for 1000 ft of hose as follows: 750 ft of 4” hose @ $8.00 per foot plus 250 ft of 2” hose @ $4.50 per foot plus inflation to 2007).

CIP Recommendation:	Replace fire hose as requested by the Fire Department.

Comments:	Department currently has 4600 ft of 2” hose for interior fire fighting and 3500 ft of 4” hose for water supply.

Project:			Replace fire engine #1

Acquisition Year Requested:	2008

Anticipated Lifespan:		20 to 25 years

CIP Priority:			Urgent

Estimated Cost:		$298,541

CIP Recommendation:	Purchase the vehicle in 2008 under a lease-purchase plan spreading the payments over four years beginning in 2008.

Comments:	Replace 1976 fire engine that has exceeded its lifespan as an emergency vehicle.  Fire Department is working on obtaining a 95% Firefighter’s Assistance Grant from FEMA, but there’s only a 50% chance of obtaining it.

Project:			Replace tanker

Acquisition Year Requested:	2011

Anticipated Lifespan:		20 to 25 years

CIP Priority:			Necessary

Estimated Cost:		$228,498

CIP Recommendation:	Purchase the vehicle in 2011 under a lease-purchase plan spreading the payments over four years beginning in 2011.

Comments:	Replace 1986 fire engine that will be 25 years old; its anticipated lifespan.

Project:			Replace existing rescue vehicle

Acquisition Year Requested:	2015

Anticipated Lifespan:		10 years

CIP Priority:			Necessary

Estimated Cost:	$24,228 + third and fourth year’s payments subsequent to 2016 (beyond the range of this CIP)

CIP Recommendation:	Purchase the vehicle in 2015 under a lease-purchase plan spreading the payments over four years beginning in 2015.

Comments:	Acquire used ambulance with diesel and 4WD to use as rescue vehicle for patient care.  Continue to use existing vehicle to haul heavy equipment.

Project:			Replace existing extrication equipment

Acquisition Year Requested:	2015

Anticipated Lifespan:		20 to 30 years

CIP Priority:			Necessary

Estimated Cost:		$20,162

CIP Recommendation:	Can hold off purchasing the equipment until 2015.

Comments:	Replace present jaws tools, an improved first generation extrication tool, with lighter more versatile and simpler to maintain and operate.  This equipment will need an overhaul in about five years to replace gaskets, etc.  This overhaul is expected to cost less than $5000.

Project:	Replace turn-out gear (PPE - personal protective equipment)

Acquisition Year Requested:	2015

Anticipated Lifespan:		10 to 15 years

CIP Priority:			Necessary

Estimated Cost:		$60,487

CIP Recommendation:	Can hold off purchasing the gear until 2015.

Comments:	Replace personal protective equipment that has been subjected to wear and tear and has less protective qualities.  Replacement equipment to include helmet, hood, coat, pants, gloves and boots.

Project:			Vehicle for full-time Fire Chief

Acquisition Year Requested:	2015

Anticipated Lifespan:		4 to 5 years

CIP Priority:			Necessary

Estimated Cost:	$20,163 + third and fourth year’s payments subsequent to 2016 (beyond the range of this CIP)

CIP Recommendation:	Purchase the vehicle in 2015 under a lease-purchase plan spreading the payments over four years beginning in 2015.

Comments:	To add vehicle for new full-time Fire Chief.

Project:			Replace fire engine #3

Acquisition Year Requested:	2025

Anticipated Lifespan:		25 years

CIP Priority:			(Future)

Estimated Cost:		$250,000 (in 2006 $)

CIP Recommendation:	(Future purchase)

Comments:	Replace 2000 fire engine that will have reached the end of its anticipated lifespan as an emergency vehicle.

Project:			Replace SCBA (self-contained breathing apparatus)

Acquisition Year Requested:	2020

Anticipated Lifespan:		10 to 15 years

CIP Priority:			(Future)

Estimated Cost:		$75,000 (in 2006 $)

CIP Recommendation:	(Future purchase)

Comments:	Existing gear will have been exposed and subjected to extreme conditions causing wear and tear, requiring excessive overhaul.

Project:			Replace fire department roof

Acquisition Year Requested:	2025

Anticipated Lifespan:		30+ years

CIP Priority:			(Future)

Estimated Cost:		TBD

CIP Recommendation:	(Future purchase)

Comments:	Replace asphalt shingles with metal roofing.  This will be the expected lifespan of present roofing and metal should last longer and hopefully eliminate snow load and ice build-up that presently occurs and requires occasional remedy.

Project:			Replace rescue boat

Acquisition Year Requested:	2035

Anticipated Lifespan:		30 years

CIP Priority:			(Future)

Estimated Cost:		$12,000 (in 2005 $)

CIP Recommendation:	(Future purchase)

Comments:	Replace rescue boat due to age, condition, maintenance costs insuring proper operation in an emergency.

Project:			Replace emergency generator

Acquisition Year Requested:	2035

Anticipated Lifespan:		30 years

CIP Priority:			(Future)

Estimated Cost:		$18,000 (in 2005 $)

CIP Recommendation:	(Future purchase)

Comments:	Replace emergency generator to power the firehouse during power failure and insure proper fire department operation in an emergency.

Note also that the Fire Department is obtaining 28 each 2-way radios from a Homeland Security federal grant.  Some additional chargers may be required, but will not exceed the $5000 threshold for a capital project.

Town Clerk

Project:			Provide new facility for town clerk’s office.

Acquisition Year Requested:	2010

Anticipated Lifespan:		30 to 40 years

CIP Priority:			Desirable, but requires additional research

Estimated Cost:		23,196 (for use of an existing facility)

CIP Recommendation:	Town clerk needs additional space for files and records and must upgrade space to meet electrical code.  Possibly use the upstairs of the old town office.  Research the entire issue of providing additional space in the future for the Tax Collector’s office, Town Clerk’s office, the Police Department and the Parks and Recreation Department.

Comments:	Coordinate the possible re-use of existing space and the renovation and/or acquisition of new space for the four departments mentioned above.  Town clerk’s office should consider scanning records to store them electronically.

Project:			Fire-proof record storage cabinets

Acquisition Year Requested:	2007

Anticipated Lifespan:		20 years

CIP Priority:			Urgent

Estimated Cost:		$8,498

CIP Recommendation:	Fire-proof storage must be provided for critical town records.

Comments:	Current records are not fully protected against fire and/or water damage.

Tax Collector

Project:			Provide new facility for tax collector’s office.

Acquisition Year Requested:	2010

Anticipated Lifespan:		30 to 40 years

CIP Priority:			Desirable, but requires additional research

Estimated Cost:		23,196 (for use of an existing facility)

CIP Recommendation:	Tax Collector needs additional space for files and records and must upgrade space to meet electrical code.  Possibly use the upstairs of the old town office.  Research the entire issue of providing additional space in the future for the Tax Collector’s office, Town Clerk’s office, the Police Department and the Parks and Recreation Department.

Comments:	Coordinate the possible re-use of existing space and the renovation and/or acquisition of new space for the four departments mentioned above.  Tax Collector’s office should consider scanning records to store them electronically.

Project:			Fire-proof record storage cabinets

Acquisition Year Requested:	2007

Anticipated Lifespan:		20 years

CIP Priority:			Urgent

Estimated Cost:		$8,498

CIP Recommendation:	Fire-proof storage must be provided for critical town records.

Comments:	Current records are not fully protected against fire and/or water damage.

Administrative Department

Project:			Replace windows in town office building

Acquisition Year Requested:	2007

Anticipated Lifespan:		TBD

CIP Priority:			Necessary

Estimated Cost:		$22,963 ($550 per window in 2005 $)

CIP Recommendation:	This is a second-level priority, but should be implemented in 2007.  Existing windows cause extreme drafts resulting in additional heating costs.

Comments:	Replace with new windows, but retain the look of the existing historical windows.

Project:	Replace boilers; upgrade HVAC in town office building

Acquisition Year Requested:	2007

Anticipated Lifespan:		TBD

CIP Priority:			Urgent

Estimated Cost:		$61,852

CIP Recommendation:	This should be implemented in 2007.

Comments:	There are presently four different types of heating in the building (oil, steam, electric and gas) and some are very old.  Estimate provided by Allen & Mathewson (6/05) includes removing old steam boiler and water heater.  HVAC estimate provided verbally by Bill Harper (6/05).  Retrofit with new system and add two new above ground oil tanks.  A/C estimate provided by Bill Harper (6/05) includes one air handler in the attic for the top floor and one the basement for the first and second floors (no drop ceilings in second floor - would be more work).

Project:			Parking lot lights

Acquisition Year Requested:	2007

Anticipated Lifespan:		TBD

CIP Priority:	Urgent

Estimated Cost:		$5,304

CIP Recommendation:	Should be implemented in 2007.

Comments:	Lighting is inadequate and can lead to potentially dangerous situations.

Project:			Elevator in town office building

Acquisition Year Requested:	2009

Anticipated Lifespan:		TBD

CIP Priority:	This project is required to satisfy handicapped access statutes, but requires further research.

Estimated Cost:		$108,207

CIP Recommendation:	This is a ‘commitment’ to satisfy legal requirements, but requires additional research before implementation.

Comments:	Elevator instead of stair-lift.  Includes external shaft (see below).  Estimated cost provided by Bill Harper (6/05) is for a Limited Use / Limited Access elevator (LULA) and a waiver may be required for its use.  LULA will accommodate two persons including one in a wheelchair.  LULA is $40,000 + $25,000 for external elevator shaft (in 2005 $).  A 6-8 person elevator would be $74,000 + 25,000 for external elevator shaft (in 2005 $).

Project:			Sprinkler system in town office building

Acquisition Year Requested:	2010

Anticipated Lifespan:		TBD

CIP Priority:	This project is required by safety statutes, but requires further research.

Estimated Cost:		$84,450

CIP Recommendation:	This is a ‘commitment’ priority, but should be implemented in 2010.

Comments:	Estimate provided by Bill Harper (6/05).  Must determine if this estimate includes the 12,000 - 14,000 gallon storage tank and fire pump required.

Project:			Sprinkler system in meeting house

Acquisition Year Requested:	2011

Anticipated Lifespan:		TBD

CIP Priority:	This project is required by safety statutes, but requires further research.

Estimated Cost:		$86,925

CIP Recommendation:	This is a ‘commitment’ priority, but should be implemented in 2011.

Comments:	Estimate provided by Bill Harper (6/05).  Must determine if this estimate includes the 12,000 - 14,000 gallon storage tank and fire pump required.

Project:			Re-do walkway from parking lot

Acquisition Year Requested:	2006

Anticipated Lifespan:		TBD

CIP Priority:	Urgent

Estimated Cost:		$21,218

CIP Recommendation:	Required to satisfy safety statutes.

Comments:	Walkway to be a ramp and moved away from the road.  Estimate includes demolition of old ramp, install new ramp and landscaping.  Good gravel base, special concrete and sealer.  Wide enough for trackless.  Town to do demolition and landscaping.

Library

Project:	Add shelving and countertops in Librarian’s office, main floor workroom and adult section

Acquisition Year Requested:	2007

Anticipated Lifespan:		50 years

CIP Priority:			Necessary

Estimated Cost:		$6,365

CIP Recommendation:	Implement in 2007

Comments:	More bookshelves and workspace are necessary.

Project:	Inspect and recommend roof maintenance

Acquisition Year Requested:	2007

Anticipated Lifespan:		(N/A)

CIP Priority:			Urgent

Estimated Cost:		$5,150

CIP Recommendation:	Implement in 2007 to determine condition of roof.

Comments:	Slate roof on original building is almost 100 years old.

Project:	Repair or replace roof on original building

Acquisition Year Requested:	TBD

Anticipated Lifespan:		50 to 75 years

CIP Priority:			(Future) - time frame indeterminate

Estimated Cost:		$38,255 (if implemented in 2009)

CIP Recommendation:	Requires additional research to determine condition of roof.

Comments:	Slate roof on original building is almost 100 years old.

Project:			Pave parking lot

Acquisition Year Requested:	(Future)

Anticipated Lifespan:		50 years

CIP Priority:			Deferrable

Estimated Cost:		$3,000

CIP Recommendation:	Present parking area is serviceable.

Comments:	Too small to be included in CIP.

Project:			Signage

Acquisition Year Requested:	(Future)

Anticipated Lifespan:		50 years

CIP Priority:			Deferrable

Estimated Cost:		$4,000

CIP Recommendation:	Can be deferred or acquired in Library’s budget.

Comments:	Too small to be included in CIP.  Signage for outdoor sign, “Ann Geisel Wing”, “Velma Stone Childrens’ Room”.  Also a benefactor’s recognition sign for all major donations (personal, company and foundations).

Parks and Recreation

Project:			Enhance / update Oak Park playground

Acquisition Year Requested:	2007

Anticipated Lifespan:		(varies)

CIP Priority:	Urgent and ‘committed’ (to comply with handicapped access)

Estimated Cost:		$42,436

Possible Funding Source:	Crotched Mountain Rehabilitation center should be contacted to see what they can provide.

CIP Recommendation:	Implement in 2007

Comments:	Improve safety.  Use plastic vs. wood.

Project:			Enlarge office space

Acquisition Year Requested:	2008

Anticipated Lifespan:		TBD

CIP Priority:			Desirable, but requires more research

Estimated Cost:		$43,713

CIP Recommendation:	Possibly use a portion of the old town office.  Research the entire issue of providing additional space in the future for the Tax Collector’s office, Town Clerk’s office, the Police Department and the Parks and Recreation Department.

Comments:	Coordinate the possible re-use of existing space and the renovation and/or acquisition of new space for the four departments mentioned above.

Project:			Pave Oak Park walking track

Acquisition Year Requested:	2010

Anticipated Lifespan:		TBD

CIP Priority:	Deferrable

Estimated Cost:		$23,195 (very rough estimate)

Possible Funding Source:	Crotched Mountain Rehabilitation center should be contacted to see what they can provide.

CIP Recommendation:	(Possible future implementation)

Comments:	Currently the track needs to have weed killer applied every year.  Paving would make it easier to maintain.  Plowing would be easier.  Less spring clean-up.

Project:			Construct fitness stations along Oak Park track

Acquisition Year Requested:	2011

Anticipated Lifespan:		TBD

CIP Priority:	Deferrable

Estimated Cost:		$7,760

CIP Recommendation:	(Possible future implementation)

Comments:	Install 12 - 13 fitness stations.  Would attract more users.

Project:			Construct permanent hockey rink

Acquisition Year Requested:	2013

Anticipated Lifespan:		TBD

CIP Priority:	Additional research required

Estimated Cost:		$38,007 (very rough estimate)

CIP Recommendation:	(Possible future implementation)

Comments:	Current temporary rink does not work (leaks).  Cost of replacing plastic liner is $150 per year.  Permanent rink would allow for roller skating in summer.

Project:			Replace kiosks

Acquisition Year Requested:	2007

Anticipated Lifespan:		(unknown)

CIP Priority:	‘Inconsistent’

Estimated Cost:		$1,600

Possible Funding Source:	N/A

CIP Recommendation:	Too small to be included in CIP.

Comments:	Replace kiosks on meeting house lawn, at Oak Park and at Sunset Lake Beach.

Highway Department - Roads

Notes:	Road project’s implementation dates subject to traffic count changes.

The following algorithm was created in 2005 to provide a rough estimate of road projects.  Values for each parameter will change as a function of the specific project (e.g. number of culverts), but this algorithm provided a ball-park figure:

Base and top coat:	$100,000 per mile

Reclaim:		$10,000 per mile

Culverts:		$5,000 per mile

Additional gravel:	$10,000 per mile

----------------------

Total:			$125,000 per mile (in 2005 $)

Greenfield’s road agent, Wyatt ‘Duffy’ Fox, estimates that the cost of material has increased by 25% over last year.  This results in an overall increase of approximately 22% for road maintenance.

There are 13 miles of paved town roads in Greenfield and 27 miles of dirt roads (excludes state maintained roads).  The following projects are needed to keep pace with required maintenance.

Project:			1.25 miles of Mountain Rd.

Acquisition Year Requested:	2007

Anticipated Lifespan:		15 years

CIP Priority:			Necessary

Estimated Cost:		$188,490

CIP Recommendation:	Implement in 2007

Comments:	Reclaim, replace culverts, improve gravel base, repave

Project:			1.25 miles of Mountain Rd. to T/L

Acquisition Year Requested:	2008

Anticipated Lifespan:		15 years

CIP Priority:			Necessary

Estimated Cost:		$202,253

CIP Recommendation:	Implement in 2008

Comments:	Reclaim, replace culverts, improve gravel base, repave

Project:	1.5 miles of Slip Rd.; railroad crossing to Lakeview Cir on Zepher Lake rd.

Acquisition Year Requested:	2009

Anticipated Lifespan:		15 years

CIP Priority:			Necessary

Estimated Cost:		$250,024

CIP Recommendation:	Implement in 2009

Comments:	Reclaim, replace culverts, improve gravel base, repave

Project:			1.5 miles - Lakeview Cir to Route 31 + Gould Hill

Acquisition Year Requested:	2010

Anticipated Lifespan:		15 years

CIP Priority:			Necessary

Estimated Cost:		$257,573

CIP Recommendation:	Implement in 2010

Comments:	Reclaim, replace culverts, improve gravel base, repave

Project:			1.0 miles of Old Bennington Rd.; Forest Rd. to T/L

Acquisition Year Requested:	2011

Anticipated Lifespan:		15 years

CIP Priority:			Necessary

Estimated Cost:		$176,748

CIP Recommendation:	Implement in 2011

Comments:	Reclaim, replace culverts, improve gravel base, repave

Project:			0.5 miles of Knotwood Dr.

Acquisition Year Requested:	2012

Anticipated Lifespan:		15 years

CIP Priority:			Necessary

Estimated Cost:		$91,043

CIP Recommendation:	Implement in 2012

Comments:	Reclaim, replace culverts, improve gravel base, repave

Project:			1.0 miles of Russell Station Rd.; Route 31 to T/L

Acquisition Year Requested:	2013

Anticipated Lifespan:		15 years

CIP Priority:			Desirable

Estimated Cost:		$187,575

CIP Recommendation:	Implement in 2013

Comments:	Reclaim, replace culverts, improve gravel base, repave

DPW - Facilities

Notes:	Outdoor wood burning furnace may be added to proposed DPW projects in the future.

Greenfield spends approximately $50,000 annually for aggregate - we could consider having our own pit.

Project:			Build salt and sand shed

Acquisition Year Requested:	2008

Anticipated Lifespan:		30 years

CIP Priority:	Necessary and ‘committed’ (comply with EPA requirements)

Estimated Cost:		$143,235

CIP Recommendation:	Implement in 2008

Comments:	Reduce runoff to comply with EPA requirements.  Reduces erosion of salt.  Improves speed of access to salt and sand in inclement weather.

Project:			Security fencing

Acquisition Year Requested:	2009

Anticipated Lifespan:		25 years

CIP Priority:	Necessary

Estimated Cost:		$81,975

CIP Recommendation:	Implement in 2009.  Reduces unauthorized access and increases safety and security of the site.

Comments:	Deploy a security fence around perimeter to limit exposure.  Reduce liability for easy access to dangerous equipment.  Should be installed before surrounding residential lots are developed.

Project:			New DPW building

Acquisition Year Requested:	2009

Anticipated Lifespan:		30+ years

CIP Priority:	Desirable

Estimated Cost:		$570,105 (plus last two years of 10-year bond)

CIP Recommendation:	Implement in 2009

Comments:	Includes land acquisition + building construction (seven bays, office, etc.).

DPW - Vehicles

Project:			Purchase F-550 to replace small dump truck

Acquisition Year Requested:	2006 (Four-year lease purchase began last year)

Anticipated Lifespan:		10 years

CIP Priority:	Urgent and ‘committed’ (need F-550 to get GVW weight rating required)

Estimated Cost:		$59,114 (for final three years of lease-purchase).

CIP Recommendation:	(N/A)

Comments:	(Vehicle already purchased).

Project:			Purchase Caterpillar 920 loader to replace existing loader

Acquisition Year Requested:	2007

Anticipated Lifespan:		15 years

CIP Priority:			Urgent

Estimated Cost:		$168,985

CIP Recommendation:	Purchase the vehicle in 2007 under a lease-purchase plan spreading the payments over four years beginning in 2007.

Comments:	Existing vehicle purchased in 1978.

Project:	Purchase Caterpillar 4WD backhoe to replace existing backhoe

Acquisition Year Requested:	2009

Anticipated Lifespan:		10 years

CIP Priority:			Necessary

Estimated Cost:		$143,456

CIP Recommendation:	Purchase the vehicle in 2009 under a lease-purchase plan spreading the payments over four years beginning in 2009.

Comments:	Existing vehicle purchased in 1999.

Project:			Replace International Tandem dump truck

Acquisition Year Requested:	2012

Anticipated Lifespan:		12 years

CIP Priority:			Necessary

Estimated Cost:	$176,289

CIP Recommendation:	Purchase the vehicle in 2012 under a lease-purchase plan spreading the payments over four years beginning in 2012.

Comments:	Existing vehicle purchased in 2002.

Project:			Replace Mt. Trackless

Acquisition Year Requested:	2015

Anticipated Lifespan:		12 years

CIP Priority:			Necessary

Estimated Cost:	$48,307 + third and fourth year’s payments subsequent to 2016.

CIP Recommendation:	Purchase the vehicle in 2015 under a lease-purchase plan spreading the payments over four years beginning in 2015.

Comments:	Existing vehicle purchased in 2003.

Project:			Replace grader

Acquisition Year Requested:	(Future, 2018)

Anticipated Lifespan:		15 years

CIP Priority:			Future purchase

Estimated Cost:	$158,000 (in 2005 $)

CIP Recommendation:	Future purchase

Comments:	Existing vehicle purchased in 2003.

Project:			Replace International 6 wheel dump truck

Acquisition Year Requested:	(Future, 2016)

Anticipated Lifespan:		12 years

CIP Priority:			Future purchase

Estimated Cost:	$105,000 (in 2005 $)

CIP Recommendation:	Future purchase

Comments:	Existing vehicle purchased in 2004.

Recycling Center

Project:			Paving

Acquisition Year Requested:	2009

Anticipated Lifespan:		TBD

CIP Priority:	Needs additional research

Estimated Cost:		$56,290

CIP Recommendation:	Research actual need and type of material to be used

Comments:	Paving of existing approach, unloading and exit area.

Project:			New storage building

Acquisition Year Requested:	2011

Anticipated Lifespan:		30+ years

CIP Priority:	Needs additional research

Estimated Cost:		$63,270

CIP Recommendation:	Additional research needed to determine actual requirement.

Comments:	Construct 50’ x 80’ recyclable storage building.  ‘Full load’ capacity.  Will also allow storage during price fluctuations.

Project:			Fork lift

Acquisition Year Requested:	2014

Anticipated Lifespan:		10 years

CIP Priority:	Needs additional research

Estimated Cost:	$36,353 + fourth year’s payments subsequent to 2016 (beyond the range of this CIP).

CIP Recommendation:	Additional research needed to determine actual need.

Comments:	Existing forklift purchased in 2004.

Project:			Replace waste oil furnace

Acquisition Year Requested:	2024

Anticipated Lifespan:		20 years

CIP Priority:			(Future)

Estimated Cost:		$7,500 (in 2005 $)

CIP Recommendation:	(Future purchase)

Comments:	Existing furnace purchased in 2004.

Project:			Replace boiler

Acquisition Year Requested:	2032

Anticipated Lifespan:		30 years

CIP Priority:			(Future)

Estimated Cost:		$20,000 (in 2005 $)

CIP Recommendation:	(Future purchase)

Comments:	Existing boiler purchased in 2002.

Project:			Replace compactor

Acquisition Year Requested:	2020

Anticipated Lifespan:		20 years

CIP Priority:			(Future)

Estimated Cost:		$35,000 (in 2005 $)

CIP Recommendation:	(Future purchase)

Comments:	Existing compactor purchased in 2000.

Project:			Replace building

Acquisition Year Requested:	2030

Anticipated Lifespan:		30 years

CIP Priority:			(Future)

Estimated Cost:		$100,000 (in 2005 $)

CIP Recommendation:	(Future purchase)

Comments:	Existing structure completed in 2004.

Appendix F - Projects recommended by the CIP committee for 2007 - 2016 with a priority of ‘Urgent’

| Department | Est Cost in 2006 $ | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Police | $30,797 |  | $8,169 | $8,659 | $9,182 | $9,729 |  |  |  |  |  | $35,739 |
| Fire | $277,125 | $20,214 | $68,238 | $72,332 | $76,700 | $81,271 |  |  |  |  |  | $318,755 |
| Town Clerk | $8,250 | $8,498 |  |  |  |  |  |  |  |  |  | $8,498 |
| Tax Collector | $8,250 | $8,498 |  |  |  |  |  |  |  |  |  | $8,498 |
| Admin | $85,800 | $88,374 |  |  |  |  |  |  |  |  |  | $88,374 |
| Library | $5,000 | $5,150 |  |  |  |  |  |  |  |  |  | $5,150 |
| Highway - Roads |  |  |  |  |  |  |  |  |  |  |  |  |
| DPW - Facilities |  |  |  |  |  |  |  |  |  |  |  |  |
| DPW - Vehicles | $222,100 | $57,191 | $60,623 | $64,283 | $46,002 |  |  |  |  |  |  | $228,099 |
| Recycling Center |  |  |  |  |  |  |  |  |  |  |  |  |
| Parks and Recreation | $41,200 | $42,436 |  |  |  |  |  |  |  |  |  | $42,436 |
| Total | $678,522 | $230,361 | $137,030 | $145,274 | $131,884 | $91,000 |  |  |  |  |  | $735,549 |
| NOTES: |  |  |  |  |  |  |  |  |  |  |  |  |
| See notes on each department's spreadsheet. |  |  |  |  |  |  |  |  |  |  |  |  |
| Town Clerk and Tax Collector have submitted identical proposals. |  |  |  |  |  |  |  |  |  |  |  |  |
| Sources for funding projects (e.g. bond issue(s), grants, etc.) are being investigated. |  |  |  |  |  |  |  |  |  |  |  |  |
| Costs adjusted for an estimated 3% annual rate of inflation. |  |  |  |  |  |  |  |  |  |  |  |  |
| Inflation factors: |  | 1.030 | 1.061 | 1.093 | 1.126 | 1.159 | 1.194 | 1.230 | 1.267 | 1.305 | 1.344 |  |
| Vehicles purchased on a four-year lease-purchase plan adjusted for an estimated 6% annual rate of interest. |  |  |  |  |  |  |  |  |  |  |  |  |
| Year of lease: |  | 1st | 2nd | 3rd | 4th |  |  |  |  |  |  |  |
| Multiplier: |  | 1.000 | 1.060 | 1.124 | 1.191 |  |  |  |  |  |  |  |

Appendix G - Projects recommended by the CIP committee for 2007 - 2016

with a priority of ‘Urgent’ plus a priority of ‘Necessary’

| Department | Est Cost in 2006 $ | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Police | $123,188 |  | $8,169 | $8,659 | $17,851 | $18,918 | $9,744 | $19,795 | $10,038 | $20,692 | $21,930 | $135,796 |
| Fire | $585,225 | $20,214 | $68,238 | $72,332 | $76,700 | $133,499 | $55,362 | $58,704 | $62,204 | $102,198 | $22,842 | $672,293 |
| Town Clerk | $8,250 | $8,498 |  |  |  |  |  |  |  |  |  | $8,498 |
| Tax Collector | $8,250 | $8,498 |  |  |  |  |  |  |  |  |  | $8,498 |
| Admin | $108,094 | $111,337 |  |  |  |  |  |  |  |  |  | $111,337 |
| Library | $11,180 | $11,515 |  |  |  |  |  |  |  |  |  | $11,515 |
| Highway - Roads | $1,059,875 | $188,490 | $202,253 | $250,024 | $257,573 | $176,748 | $91,043 |  |  |  |  | $1,166,131 |
| DPW - Facilities | $737,000 |  | $143,235 | $139,576 | $61,057 | $64,721 | $68,604 | $72,720 | $77,083 | $81,708 | $86,611 | $795,315 |
| DPW - Vehicles | $549,200 | $57,191 | $60,623 | $97,073 | $80,759 | $36,856 | $79,351 | $42,716 | $45,279 | $71,446 | $24,857 | $596,151 |
| Recycling Center |  |  |  |  |  |  |  |  |  |  |  |  |
| Parks and Recreation | $41,200 | $42,436 |  |  |  |  |  |  |  |  |  | $42,436 |
| Total | $3,231,462 | $448,179 | $482,518 | $567,664 | $493,940 | $430,742 | $304,104 | $193,935 | $194,604 | $276,044 | $156,240 | $3,547,970 |

Appendix H - References

- Capital Improvements Programming Handbook, Southern New Hampshire Planning Commission, Manchester New Hampshire.

- 1970: US Census.

- 1971 - Present: Office of State (NH) Planning Estimates.

- NH Office of Energy & Planning.

Note: The Capital Improvements Program for 2006 through 2015, Greenfield, New Hampshire dated 9/26/05 was the initial source for the current update.