SSBC Minutes

Date:		Sep 14, 2010

Location:	North Reading Middle School Library

Attending members: Chuck Carucci, Laurie Witts, Don Kelliher, Steven Nathan, Gerry Venezia, Ed Stiles, Sean Delaney, Cliff Bowers, Gregg Doble, Helen Maynard, Janene Imbriano

Attending Associates members:  Jack Pecora, Phil Dardeno, Dan McInnis

Non-voting Members:  Wayne Hardacker (Super. Bldgs & Grnds), Jon Bernard (HS Principal), John Faucher (MS principal), Kathleen Willis (Superintendent of Schools)

Visitors: Brad Dore (Dore & Whittier), Jeff Yull

Absent: Greg Balukonis,

Meeting opened 6.40 by Chairman Chuck Carucci

- Supt Report

  - Sup Willis attended a MSBA Enrollment Teleconf. with Principal Bernard

  - MSBA proposed estimate of students at 700at the High School

  - 13 Sept follow up meeting at which time K Willis argued enrollment should be much higher.  740 HS Students is the current figure

  - Feasibility Study Agreement (FSA)

    - 4 exhibits A-D (4 handouts )

    - Exhibit A – Feasibility Study Budget

    - Exhibit B –Scope of the Feasibility Study(including schedule of deliverables)

    - Exhibit C –Feasibility Study Schedule

    - Exhibit D –Reimbursement Rate

- Discussion on Enrolment figure.  It seems firm, but later in the process there will be an opportunity to re-visit the issue

- Discussion on whether to accept the MSBA figure or negotiate for a higher number.  Negotiations will take more time, and getting started with the process could be advantageous

- Motion made to accept the MSBA number (740  students)made by Steven N

  - 2nd by Sean D

  - Vote: Yes (Unanimous) -Janene, Helen, Laurie, Steve, Gregg, Ed, Gerry, Sean, Don, Chuck

- Further discussion on Exhibit A

  - $1,000,000 approved by Town Meeting

    - OPM 	$200K

    - Design	$700K

    - Enviro	$50K

    - Other 	$50K

- Discussion on OPM hiring

  - Hiring is not low-bid based

  - Hiring is solely on Qualification based

- Brad Dore will review other projects the same size and scope to see if the appropriations are within reason

- Discussion on Exhibit C

  - Possible time line

    - March 2010	MSBA approval to move forward

    - June 2011	Complete Feasibility Study with design

    - Aug 2011	Budget & Scope confirmed

    - Aug 2011	MSBA approval of project

    - Oct 2011	Town meeting vote

    - Nov 2011	Town wide vote

- It was noted that Jon Bernard needs to be officially appointed to the SSBC, Sean to get this on the Selectman’s meeting possibly 27 Sep joint SC & BOS meeting

- 20 Sep School Committee meeting to accept enrollment figure

- Motion to accept minutes from 15 Jun meeting by Sean, and 2nd by Gregg

  - Vote unanimous to accept

- Motion made by Chuck to create a Media relations committee, to be head by Janene

  - 2nd by Gerry V

  - Approved unanimoius

- next meeting 19 Oct at 6.30 pm in NRMS library.

- Motion to adjourn made by Sean

  - 2nd by Gerry V

- Meeting closed 8.20p