## Sheet1
FY16 CAPITAL IMPROVEMENT PROJECTS | (General Government) | As of September 1, 2015
COMPLETION
TITLE | STATUS | DATE | APPROPRIATION
PUBLIC WORKS
Paving Chapter 90 | Spring of 2016 project. | 2016-07-01 | 451000
Paving Non Ch. 90 | Handicapped ramps began Sept. 7; paving delayed until Spring | 2015-11-01 | 475000
Open Space Improvements | On-going. | 2016-07-01 | 150000
DPW Fleet Replacement Program | 10-wheel dump truck ordered off state bid list. | 2015-12-01 | 160000
Water Main Replacement | Completed with exception of punch list. | COMPLETED | 250000
Public Building Maintenance | On-going. | 2016-07-01 | 100000
Wastewater Infrastructure | On-going. Funding is supporting Administrative Consent Order. | Unknown | 81000
Cassidy Park Seawater Outflow | Spring of 2016 project. | 2016-07-01 | 20000
Surf Rake | Rake, tractor, equipment ordered and expected by end of Oct. | 2015-09-30 | 85000
POLICE DEPARTMENT
Technology Upgrade | Server install completed. Telephone recorder install completed. | COMPLETED | 24563
Radio Upgrade | Radio receiver ordered | 2015-10-01 | 24400
FIRE DEPARTMENT
Command Vehicle | Being ordered from MHK; delivery in 8 to 10 weeks. | 2016-01-01 | 42500
Wired Fire Alarm Systems | Reviewing immediate wiring issues. | 2016-06-30 | 25000