## Sheet1
FY16 CAPITAL IMPROVEMENT PROJECTS | (General Government) | As of March 1, 2016
COMPLETION
TITLE | STATUS | DATE | APPROPRIATION
PUBLIC WORKS
Paving Chapter 90 | Spring of 2016 project. | 2016-07-01 | 451000
Paving Non Ch. 90 | 23 handicapped ramps have been installed to date. | 2016-06-01 | 475000
Open Space Improvements | On-going. | 2016-07-01 | 150000
DPW Fleet Replacement Program | 10-wheel dump truck purchased and received. | COMPLETED | 160000
Water Main Replacement | Completed with exception of punchlist. | COMPLETED | 250000
Public Building Maintenance | On-going. | 2016-07-01 | 100000
Wastewater Infrastructure | This will be used to repair the Windsor South Lift Station. | Unknown | 81000
Cassidy Park Seawater Outflow | Spring of 2016 project. | 2016-07-01 | 20000
Surf Rake | Rake, tractor, equipment purchased and received. | COMPLETED | 118000
POLICE DEPARTMENT
Technology Upgrade | Server install completed. Telephone recorder install completed. | COMPLETED | 24563
Radio Upgrade | Radio repeater/transmitter installed. | COMPLETED | 24400
FIRE DEPARTMENT
Command Vehicle | Expected delivery on March 8th. | 2016-03-08 | 42500
Wired Fire Alarm Systems | Pole changes wiring plant issues ongoing. | 2016-06-30 | 25000