Community and Economic Development Authority

# Board Meeting Minutes

# 5:00 PM, July 9, 2012

TOWN OF WAREHAM 	            Wines and More, Wareham Crossing

54 Marion Road

Wareham, MA  02571

Present: Jean Connaughton, Sandra Besse, Robert Fitchenmayer, Rudy Santos, David Smith, and Salvador Pina

Not Present:	Jo Jeffries, Jennifer Petersen, and Stephen Holmes

Also Present: 	David Fleming, Ellyne Fleshner, Allison Yee, and Sean Crump

Call to Order: Chairman Connaughton called the meeting to order at 5:01 PM.

Old Business:

- Approval of CEDA Board Meeting Minutes – June 4, 2012:

Ms. Besse motioned to approve the minutes of the June 4, 2012 CEDA Board Meeting. Mr. Smith seconded the motion. The Motion passed 3-0-2

- Streetscape:

Mr. Pina provided an update of the Streetscape project Phase 1 Activities. He noted that all major activities were completed on June 6, 2012. The construction team is scheduled to walk the site on June 11, 2012 to identify any final punch list items.

Recommendation: Close out Phase 1 of the project, review the project with the engineer and Clerk of the Works for lessons learned, and review the remaining phases of the project to determine if any changes are required.

Action Required: No Action Required by the Board

- Stormwater Grant: Mr. Pina submitted a grant in collaboration with the Planning Department’s Conservation Agent, Mr. Pichette on June 28, 2012 for $20,000 for Stormwater Plan Design Assistance. As the grant was for Stormwater Plan Design Assistance, it was the only eligible activity where no match was required.

Recommendation: None

Action Required: No Action Required by the Board

- Certificate of Vote: The Certificate of Vote was signed by CEDA Board Chair, Ms. Connaughton and forwarded on to the Board of Selectmen for approval at the July 10, 2012 Board of Selectmen meeting.

Recommendation: None

Action Required: Ms. Connaughton and Mr. Pina will represent the CEDA Board at the Board of Selectmen meeting on July 10, 2012.

- Police Department Traffic Signs: The Police Department has received the two electronic mobile signs requested. Mr. Pina is working with Chief Stanley on a press release and photo opportunity for the Board Chair.

Recommendation: None

Action Required: No Action Required by the Board

- Small Business Loan Pool: The Small Business Loan Pool has been established (see attached article) and Mr. Pina is working on marketing material to present the program to the downtown businesses in the fall.

Recommendation: Develop marketing material for distribution to businesses in the target area in the fall.

Action Required: Mr. Pina will present marketing material to the Board after it is developed.

New Business

- Financial Report Summary (see attached)

  - Housing Development Support Program (361 Main) – This Grant has been closed

  - FY’08 & FY’09 Grants have been closed.

  - FY'10 Grant is 88% expended as of 7/03/12. Remaining projects include: Recovery Road, Streetscape, Turning Point, and the Code Enforcement Program.

  - FY'11 Grant is 14% Expended as of 7/03/12.

  - FY'12 Grant has been approved by DHCD. The CEDA Office has submitted a Request for Release of Funds.

  - Revenue as of 7/03/12:

    - Program Income = $58,219.66

    - Recovery Road = $33,906.71

    - Bay Pointe = $110, 424.37

    - Info Booth = $7,427.85

Recommendation: None

Action Required: No Action Required by the Board

- Reserve Fund – The Chair entertained a discussion regarding CEDA’s revenue. Areas of concern include: the need to develop a reserve fund, criteria for disbursement of funds, and a schedule for receiving requests for funds.

Recommendation: The CEDA Board asked Mr. Pina to develop a policy regarding disbursement and use of revenue

Action Required: Mr. Pina will develop a policy for review by the Board at the next meeting.

- Request for Proposals (RFP) for Public Services: Mr. Pina developed a Request for Proposals for Public Services for the FY’13 CDBG Mini-Entitlement Grant Application for review by the CEDA Board (see attached).

Recommendation: Mr. Pina recommended that the Board accept the RFP as submitted and that Mr. Pina begin the process of procuring Public Services for the FY’13 CDBG Mini-Entitlement Grant Application.

Action Required: Mr. Fitchenmayer motioned to accept the RFP as submitted and begin the process of procuring Public Services for the FY’13 CDBG Mini-Entitlement Grant Application. Mr. Santos seconded the motion. The motion passed 5-0-0

- Certificate Training: Mr. Pina facilitated a meeting with members of the CEDA Board, the Cape Verdean Association, the Wareham School Department, Bristol Community College, and Upper Cape Cod Regional Vocational School to discuss the start-up of Certificate Training at the Hammond School in Onset. Present at the meeting representing CEDA were: Jean Connaughton, Rudy Santos, and Sandra Besse.

Recommendation: Mr. Pina recommended that the Board consider allocating funds to assist with start-up.

Action Required: The Board would like to see some training piloted before committing to providing funding for start-up. Mr. Pina will continue to work with the partnership to pilot training programs for the fall.

- Rededication of Pezzoli Square: Mr. Pina has been in discussions with Ray and Jeannie Pezzoli, the children of the Police Officer for whom Pezzoli Square is named regarding a rededication of the Square.

Recommendation: Mr. Pina recommended that the Board consider rededicating Pezzoli Square to bring attention to the beautification of the square and to the businesses downtown. Mr. Pina established a tentative date of August 17, 2012 and recommends coordinating with the Main Street Madness initiative (see below).

Action Required: The Board encouraged Mr. Pina to work on a rededication of the square.

- Main Street Madness: Concerned businesses in collaboration with the Wareham Village Association are working on a strategy to bring attention to downtown businesses through an effort they call Main Street Madness (see attached).

Recommendation: Mr. Pina recommended that the Board consider supporting this initiative through a rededication of Pezzoli Square.

Action Required: Board Chair, Connaughton will attend the next meeting of the Main Street Madness initiative to discuss how we might coordinate events.

- Stonestreet Corporation Presentation: Mr. Sean Crump, of Stonestreet Corporation, presented a plan for the redesign of the Bay Pointe entrance.

Recommendation: None

Action Required: No Action Required by the Board

- WS Development Presentation: Mr. David Fleming and Ms. Ellyne Fleshner of WS Development presented on their organization and the strategies and challenges they face managing Wareham Crossing. Mr. Fleming noted that Wareham Crossing is 95% leased. Best Buy and the Friendly’s Express have recently closed. Mr. Fleming identified the following initiatives currently scheduled:

  - Replica Lighthouses – WS Development will place two replica Lighthouses on the property for use by the public as educational use for students;

  - Wareham Gatemen – The Gatemen will be at Wareham Crossing on Thursday from 11-2 to interact with the public and sign autographs;

  - Braveheart Awards – Activities designed to highlight Special Olympians. Special guests include: Joe Andruzzi, Steve Nelson, and Maria Stefanos.

Recommendation: None

Action Required: No Action Required by the Board

Other Business

Being no other business, Mr. Fitchenmayer moved to adjourn and Mr. Santos seconded the motion. The motion passed 5-0-0.

# Meeting Adjourned at 6:57 PM